## Revisions
Clien Revision |  |  |  |  | QC Status
Sprint 4
Edit Referral >> Make the $ sign permanently visible while entering the value in the referral value text box | 0.25 | Priti |  | P | PASS
Message >> Searching based on message body too |  |  | TBD |  | TBD
Drop down on all pages changed to Modern Dropdown | Designer | Priti |  | P | Not Delivered
Referral List, Message List, Contact List should be completely clickable to view the details | 3 | Priti |  | Done | PASS
All the search bar will have 'x' icon to remove the search string and reset the listing | 4 | Rohan |  | Done | PASS
Change 'Apply' to 'Go' in the dashboard and place it to right side | Designer | Roahn |  | Done | PASS
Dashboard >> Change the Time Frame dropdown to month year picker | Designer | Rohan |  | Done | PASS | But needs some amends in CSS
Dashboard >> Make the text bold in right side bar headers | 0.25 | Jitendra |  | Done | PASS
Dasbhboard >> Make Receive, Sent, Both Radio buttons | 0.25 | Jitndra |  | P | PASS
ADD CONTACT:
Delete any allowances for texts under job title when entering (@ / #. -) etc. | 0.5 | Rohan |  | Done | PASS
Contact fields should be set up like referral fields - in the same order | 0.5 | Priti |  | P | Not Delivered
Should all referrals immediately go to contacts? That way you have all your contacts in one place | Ask client | 12
Sprint 3 - Carry forward revisions
In drop down boxes, it is possible to start typing the name of a state and it pulls up? Same with all boxes? In other works, I start typing “C” for “California” and all options that begin with “C” pop up? | 4 | priti | Sabina | P | PASS | Not done on Admin >> Business Owners
We have “download” all your referrals so a user can have a list of all his referrals | 2 | Jitendra |  | Done | PASS
Receiver should receive chat with message "live" instead of refreshing page | 6 | Jitendra | Web and Mobile | P | FAIL | Multiple comment is getting posted
On receiving new comment, message should be received in the FoxHopr Inbox | 4 | Rohan | Web and Mobile | P | PASS
Reduce the white space in all the pages to move the content upwards | 1 | Priti |  | P | PASS
Show the list of previous group members in the Team member list section wise/Show the list of previous members in the | Later |  |  |  | TBD
We have “download” all your referrals so a user can have a list of all his contacts | 2 | Jitendra |  | Done | PASS
| 27.75 | 28

## Sprint 5
Web
As a registered user I will click the billing sub-tab under account tab so that I can cancel account
Apply the Pop Up form on all the page and on every action performed.
As a registered user I will click the account tab so that I can go to the Twitter sub tab to configure it with my foxhopr account.
Update the right side bar on the website
Update the Footer Links
As a registered user I will click review tab to send review request to the referrals received.
As a registered user I will join a group and become the Group Leader and Co-leader
As a registered user I will click the partner sub-tab under contacts so that I can view the list of invited partners, search, sort and set results per page.
As a registered user I will click the account tab so that I can navigate to the Invite partner sub tab and send invitations.
As a registered user I will click the team member name under team tab to view the team member details.
As a registered user I will login in FoxHopr website so that I can check the referral status by the dollar value (Graph 3) in the Dashboard.
As a registered user I will click the billing sub-tab under account tab so that I can upgrade/downgrade my membership.
As a registered user I will re-login so that I can reactivate my account.